## query121217
Business Unit | Division | Project Name | PM | Risk Metric | Risk Mgmt | Plan Metric | Plan Status | CM Metric | Deliverables Metric | Deliverable Notes | QA Metric | QA Notes | Customer Metric | Customer Feedback | Gen'l PM/Site Status Metric | Notes | Closeout Date | Item Type | Path
Civil Programs | Civil Programs | ADS-B (Rel 1) | Shelli Debardi | No (R) | Last risk logged 6 months ago; not closed or mitigate | In Progress (Y) | Plan still in draft | In Progress (Y) | No (R) | Deliverables not uploaded since 2015; document library has unrelated items | Red | No QA approvals since 2015 | In Progress (Y) | Feedback reported in April in the Journal, but no evidence of discussion in PMRs | Yellow | Project site needs updates and completion of Plan. Ensure QA Log is used and risks are current |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | Advanced Technology Development & Prototyping | Robert Manuse | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | ASR-11 | Lee Smith | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | ASR-9 | Kelly Pashkoff | In Progress (Y) | Looks like a recent risk was added, but it's not dated by year | In Progress (Y) | Assumed that it is checked out because no documents show in the Library | In Progress (Y) | No (R) | No deliverables uploaded in 2017 | Red | PMR indicates that QA is expected, but there are no entries in this log | No (R) | There is no customer feedback indicated in the Journal, but recent issues are added. | Yellow | Check that documents are checked in. Good that PMRs are being done |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | ATS Support | Robert Manuse | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | Engility Group 1 | Samuel Ekhaus | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | ETASS/HSI Weather Programs Support | Troy Hammond | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | ISAM/SSMT | Robert Blumer | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | NASA ATD-2 | Benjamin Levy | Approved (G) | Two recent risks added, with resolution dates | In Progress (Y) | Plan has been worked; approval in the QA log is needed | Yes (G) | Yes (G) |  | Red | Plan approval needs to be documented | Yes (G) | Journal is being used consistently; no direct customer feedback yet | Green | Effort to get this site updated is good. |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | SE2025 Veracity – EVM Focal Point | Sean Osborne | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | Terminal Facilities (AJW) | Alan Wilson | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | Veracity eFast EVM | Sean Osborne | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | Agile Combat Support - HX5 | Howard Packer | In Progress (Y) | Risks have not been updated; it appears loss of personnel is a big risk | Approved (G) | Updated this year | Yes (G) | In Progress (Y) | Only two MSRs for this year are uploaded | Yellow | Plan is approved through the QA Log, but nothing else. | In Progress (Y) | Journal is being used, but it appears that issues and customer feedback should be more featured. | Yellow | Need to identify and track risks as they become issues; close as appropriate |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | DS TAT AFIT | Howard Packer | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | DS TAT AFLCMC/EZ | Howard Packer | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | DSTAT C-5 | Howard Packer | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | EPASS B2 | Howard Packer | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | EPASS Fighter-Bomber | Howard Packer | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | EPASS HQ AFMC/A4 | Michael Brown | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | EPASS: CRH | Howard Packer | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | ISR Sensors - DCS | Glen Fike | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | NAPMA Cost Sppt (Windmill) | Peter Meisl | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense National Capitol Region | NavAir 4.2 NSI | Christina Snyder | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense National Capitol Region | NAVAIR PMA 202 Support | Christina Snyder | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense National Capitol Region | ONR 03TTX | Joseph Piff | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense National Capitol Region | ONR SBIR/STTR Support | Joseph Piff | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense National Capitol Region | ONRG (London) Support | Joseph Piff | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense National Capitol Region | PEO EIS - CSA Subcontract | Joseph Piff | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | AED Fixed Wing | Nathaniel Whitfield | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | ANMP | Ed Myszka | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | Apache AED | Laura Bequette | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | FW Log | James Gaddis | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | JSIL II | James Gaddis | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | PM ASE II |  | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red | No activity on this project since August 2016; new PM has not been named |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | PM Fixed Wing II | Craig Zgraggen | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | PM UAS | Robert Hess | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | TACT | Scott Brown | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
MCR Global | Global NATO Programs | BI-SC PMC | Andrew Dreslinski | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
MCR Global | Global NATO Programs | MODSIMMET | Gary Horne | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
MCR Global | Global NATO Programs | NACMA | Joseph Helfter | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
MCR Global | Global NATO Programs | NAGSMA | Paul Torilli | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
MCR Global | Global NATO Programs | NCIA SSC3 | Donovan Pavlik | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | AICIG Bridge | Kevin Sievers | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | DMDPO | Pat Kelly | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | EPASS | Elia Sanjume | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | E-SMARTS-BAH | Pat Kelly | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | LANDMARK PS | Pat Kelly | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | MACSS TO 002 | Elia Sanjume | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | NELO CAED Support | Paul Dash | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | NELO/ONI AMOD | Paul Dash | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | R2-3G/PM EW | Dave Peters | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | RICE | Pat Kelly | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | RICE Bridge | Pat Kelly | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | Smartronix CEA | Pat Kelly | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | Support to CCOS | Pat Kelly | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | TRADOC G2 Core | Pat Kelly | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Space Programs | Space Programs | JNWC | Christina Sharp | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Space Programs | Space Programs | LLNL Integrated Project Management Development | Christopher Seemann | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Space Programs | Space Programs | MILSATCOM MC01 | Mariza Corral | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Space Programs | Space Programs | MILSATCOM MC03 Admin Support | Daniel Belden | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Space Programs | Space Programs | OASIS SATCOM | Robert Romero | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics
Space Programs | Space Programs | SNL Nuclear Weapons Project Support | Christopher Seemann | No (R) |  | No (R) |  | No (R) | No (R) |  | Red |  | No (R) |  | Red |  |  | Item | myProjects/Lists/Project Management Metrics